## Source_Index
source_id | file_name | record_type | primary_content | document_control_note
PS-41-001 | PS-41-001_project_brief_and_work_limits.pdf | PDF | project constraints, work limits, temporary works controls, dewatering limits, concrete controls | source record
PS-41-002 | PS-41-002_excavation_shoring_and_site_layout.xlsx | XLSX | stage layout, excavation geometry, shoring register, site clearances | this workbook
PS-41-003 | PS-41-003_geotechnical_borehole_and_groundwater_summary.pdf | PDF | boreholes, groundwater, inflow, monitoring triggers | source record
PS-41-004 | PS-41-004_utility_protection_and_clearance_register.csv | CSV | utility locations, clearance checks, protection requirements | source record
PS-41-005 | PS-41-005_dewatering_pump_and_monitoring_log.xlsx | XLSX | pump register, flow checks, monitoring logs, discharge quality | source record
PS-41-006 | PS-41-006_concrete_delivery_cure_and_lift_windows.pdf | PDF | concrete delivery, cure releases, lift windows | source record
PS-41-007 | PS-41-007_traffic_access_and_working_hours.csv | CSV | traffic windows, access constraints, pedestrian route, closures | source record
PS-41-008 | PS-41-008_permit_conditions_and_inspection_holdpoints.docx | DOCX | permit conditions and hold points | source record
PS-41-009 | PS-41-009_productivity_rates_and_daily_log_template.csv | CSV | productivity rates and daily log fields | source record

## Stage_Layout
stage_id | stage_name | planned_start | planned_finish | location_or_station | primary_activities | critical_dependency | noted_issue
STG-1 | mobilization_traffic_and_controls | 2026-10-05 07:00 | 2026-10-05 17:00 | 5+040 to 5+112 | traffic setup, pedestrian detour, utility locate, pump pad setup | HP-001 utility locate | traffic marshal count blank in traffic file
STG-2 | sheet_pile_installation | 2026-10-06 07:00 | 2026-10-07 15:00 | excavation perimeter | sawcut, pavement removal, sheet pile driving | vibration monitoring and utility clearance | sheet pile driving duration plus traffic constraints need review
STG-3 | brace_dewatering_and_excavation | 2026-10-08 07:00 | 2026-10-09 16:00 | pump station box | dewatering setup, brace levels, bulk excavation | HP-003 and HP-004 | dewatering setup rate is missing
STG-4 | base_slab_and_wet_well_installation | 2026-10-10 07:00 | 2026-10-14 17:00 | pump station box | base trim, blinding, base slab, wet well sections, grout | base slab cure release | planned work includes weekend period not permitted in brief
STG-5 | backfill_pavement_and_reopening | 2026-10-15 07:00 | 2026-10-16 18:00 | Brookside Road surface | backfill, granular base, asphalt, traffic removal | grout cure, asphalt weather release | granular base rate and asphalt delivery date are missing

## Excavation_Geometry
record_id | stage_id | geometry_item | length_m | width_m | depth_or_thickness_m | quantity | unit | calculation_note | status
EX-001 | STG-3 | main excavation box | 7.20 | 6.40 | 6.20 | 285.70 | m3 | 7.20 x 6.40 x 6.20 | SUPPLIED
EX-002 | STG-2 | pavement removal area | 18.50 | 8.00 | 0.00 | 148.00 | m2 | 18.50 x 8.00 | SUPPLIED
EX-003 | STG-2 | sheet-pile perimeter |  |  |  | 68.00 | m | layout perimeter count | SUPPLIED
EX-004 | STG-4 | blinding concrete | 7.20 | 6.40 | 0.18 | 8.40 | m3 | 7.20 x 6.40 x 0.18 | SUPPLIED
EX-005 | STG-4 | base slab concrete | 8.00 | 6.00 | 0.80 | 38.40 | m3 | 8.00 x 6.00 x 0.80 | SUPPLIED
EX-006 | STG-5 | backfill around wet well |  |  |  | 210.00 | m3 | recorded quantity | SUPPLIED
EX-007 | STG-5 | granular base | 16.00 | 8.00 | 0.50 | 64.00 | m3 | 16.00 x 8.00 x 0.50 | SUPPLIED
EX-008 | STG-5 | asphalt reinstatement |  |  |  | 135.00 | m2 | recorded area | SUPPLIED
EX-009 | STG-3 | trim excavation at sump | 2.40 |  | 0.35 |  | m3 | width_m field blank | OPEN

## Shoring_Register
record_id | stage_id | temporary_works_item | required_value | supplied_value | location_or_level | status_note | planning_effect
SHR-001 | STG-2 | temporary_works_design_reference | design reference required before excavation |  | all shoring | OPEN | Cannot verify design package reference from source records.
SHR-002 | STG-2 | sheet_pile_toe_embedment | 3.00 m below excavation bottom | 2.40 m below excavation bottom | toe el. 94.00 m vs bottom 96.40 m | CONFLICT | Supplied toe embedment is 0.60 m short.
SHR-003 | STG-3 | first_brace_install_depth | before excavation exceeds 1.50 m | brace installed after 2.10 m excavation | brace level 101.10 m | CONFLICT | First brace timing exceeds project limit.
SHR-004 | STG-3 | second_brace_install_depth | before excavation exceeds 3.60 m | brace installed after 3.85 m excavation | brace level 99.00 m | CONFLICT | Second brace timing exceeds project limit.
SHR-005 | STG-2 | vibration_baseline | baseline required before sheet pile driving |  | VM-01 | OPEN | Baseline reading missing in layout workbook; geotechnical file lists trigger only.
SHR-006 | STG-4 | base_formation_hold_point | acceptance before blinding | HP-005 referenced | bottom el. 96.40 m | HOLD_POINT | Gates blinding and base slab reinforcement.

## Site_Clearances
clearance_id | stage_id | clearance_item | required_value | supplied_value | calculated_variance | source_note | status
CLR-001 | STG-2/STG-3 | retained traffic lane width | 3.25 m minimum | 2.65 m | -0.60 m | 7.00 m roadway minus 4.35 m work zone | CONFLICT
CLR-002 | ALL | emergency access width | 3.50 m minimum | 3.10 m | -0.40 m | clear width beside pump and excavation barrier | CONFLICT
CLR-003 | STG-1/STG-5 | temporary pedestrian route | 1.50 m minimum | 1.20 m | -0.30 m | north sidewalk detour | CONFLICT
CLR-004 | STG-4 | crane outrigger setback from excavation edge | 1.20 m minimum | 1.25 m | 0.05 m | wet-well setting sketch | PASS
CLR-005 | STG-1 | pump generator setback from canal | 15.00 m minimum | 10.00 m | -5.00 m | pump pad sketch | CONFLICT
CLR-006 | STG-3 | access stair clear zone | 0.90 m minimum |  |  | field blank | OPEN