PS-41 Permit Conditions and Inspection Holdpoints

Brookside Road stormwater pump-station excavation - source record 008

# 1. Permit Conditions

| Permit ID | Stage | Permit area | Trigger or limit | Planning note | Condition type |
| --- | --- | --- | --- | --- | --- |
| PC-001 | ALL | In-channel and drainage work window | 2026-10-05 to 2026-10-18 | Planned work must remain within permit dates. | PERMIT |
| PC-002 | ALL | Turbidity trigger | Discharge turbidity greater than 25 NTU above background requires stop-discharge review. | Applies to all pump discharge monitoring. | PERMIT |
| PC-003 | ALL | Discharge location | Discharge only to MH-D7 with sediment treatment installed. | No alternate outfall listed. | PERMIT |
| PC-004 | STG-1/STG-4 | Fuel setback | Fuel storage and refueling at least 15 m from canal edge and drainage inlet. | Compare with dewatering setup record. | PERMIT |
| PC-005 | STG-1/STG-5 | Pedestrian route | Temporary pedestrian route at least 1.50 m clear width. | Compare with traffic staging file. | PERMIT |
| PC-006 | STG-3 | Dewatering before lower excavation | Dewatering operational before excavation below groundwater elevation. | Linked to HP-004. | PERMIT |
| PC-007 | ALL | Drawdown limit | Adjacent building well drawdown not more than 1.20 m from baseline. | Compare with monitoring log. | PERMIT |
| PC-008 | ALL | Settlement limit | Settlement trigger is 8.0 mm. | Compare with settlement readings. | PERMIT |
| PC-009 | ALL | Condition type | condition_type field blank. | Open permit metadata field. |  |
| PC-010 | ALL | Sediment control inspection | Inspect daily and after rainfall greater than 10 mm. | Linked to HP-008. | PERMIT |
| PC-011 | ALL | Forecast data source | forecast_source field blank. | Weather trigger source not named. |  |

# 2. Permit Observation Log

| Log ID | Date | Observation | Supplied value | Status | Owner |
| --- | --- | --- | --- | --- | --- |
| PL-001 | 2026-10-05 | Turbidity observation | background 8 NTU; discharge 21 NTU | within trigger | Environmental Monitor |
| PL-002 | 2026-10-05 | Fuel setback observation | generator tank 10 m from canal edge | conflicts with 15 m requirement | Pump Supervisor |
| PL-003 | 2026-10-05 | Pedestrian route observation | 1.20 m clear path at north sidewalk | conflicts with 1.50 m requirement | Traffic Lead |
| PL-003-DUP | 2026-10-05 | Pedestrian route observation | 1.20 m clear path at north sidewalk | duplicate of PL-003 | Traffic Lead |
| PL-004 | 2026-10-06 | Permit owner field | owner field blank | open responsibility field |  |
| PL-005 | 2026-10-06 | Drawdown observation | MW-03 drawdown 1.35 m | exceeds 1.20 m trigger | Geotechnical Monitor |

# 3. Inspection Hold Points

| Hold point ID | Stage | Activity | Trigger | Inspector role | Required record | Planning effect |
| --- | --- | --- | --- | --- | --- | --- |
| HP-001 | STG-1 | UTILITY_LOCATE | before sawcutting | Utility Coordinator | utility locate ticket | blocks sawcutting and traffic setup |
| HP-002 | STG-2 | SHEET_PILE_TOE | before excavation below pavement subbase | Temporary Works Inspector | sheet-pile driving log | confirms pile line and toe record before excavation |
| HP-003 | STG-3 | BRACE_LEVEL_1 | before excavation exceeds 1.50 m | Structural Inspector | brace torque and level log | gates deeper excavation |
| HP-004 | STG-3 | DEWATERING_OPERATIONAL | before excavation below elevation 100.60 m | Pump Supervisor | dewatering start log | gates lower excavation |
| HP-004-DUP | STG-3 | DEWATERING_OPERATIONAL | before excavation below elevation 100.60 m | Pump Supervisor | dewatering start log | duplicate of HP-004 |
| HP-005 | STG-4 | BASE_FORMATION | before blinding and base slab reinforcement | Geotechnical Engineer | formation acceptance record | gates concrete base sequence |
| HP-006 | STG-4 | PRE_POUR | before base slab concrete discharge | Construction Inspector | pre-pour checklist | gates base slab pour |
| HP-007 | STG-4 | CURE_VERIFICATION | before wet-well section setting |  | cure verification log | inspector role field is blank |
| HP-008 | ALL | DISCHARGE_MONITORING | daily before demobilization | Environmental Monitor | discharge and sediment inspection log | linked to turbidity and sediment conditions |

# 4. Daily Log Required Fields

The daily log must record weather source, rainfall forecast, groundwater levels, pump status, duty and standby pump availability, turbidity readings, traffic lane status, pedestrian route condition, access interruptions, deliveries, crew, equipment, quantities, inspections, incidents, photos, and open constraints.

# 5. Document Control Note

This source record identifies permit conditions and inspection hold points for planning review. It does not approve construction, certify temporary works, certify shoring stability, approve dewatering, certify traffic control, or authorize excavation.